## Week5 - Cost & Resources
WBS ID | Task | Resource Type | Resource Name | Quantity/Hours | Description
1.1 | Requirement Gathering | Human | Research Assistant | 35 | Discussing project requirements with team members and stakeholders
1.2 | Data Collection | Human | Research Assistant | 40 | Online data collection
2.1 | Model Design | Software | Python, Anaconda Navigator | 50 | Prepping the data and building the CNN model .
2.2 | Model Training | Software | Python, Anaconda Navigator | 50 | Training the CNN model and improving its accuracy.
3.1 | Model Evaluation | Software | Python, Anaconda Navigator | 20 | Use performance metrics to evaluate the performance and accuracy
3.2 | Dashboard Development | Software | Python, Anaconda Navigator | 30 | Build a simple and user friendly interface
4.1 | Testing & Validation | Software | Python, Anaconda Navigator | 30 | Validate both model and dashboard to ensure all is functioning properly and accurately
4.2 | Report & Presentation | Software | Word, Canva | 48 | Preparing the final report, documentation, and presentation for the project.