## Week 5 Plan
WBS ID | Task | Deliverable | Owner | Start | End | Estimated Cost
1.1 | Requirement Gathering | Requirement document | Team | 6/10 | 2025-10-08 | 700
1.2 | Data Collection | Collected dataset | Aireen | 9/10 | 13/10 | 800
2.1 | Model Design | Model architecture design | Team | 14/10 | 17/10 | 1500
2.2 | Model Training | Trained model | Yazmin | 18/10 | 23/10 | 1000
3.1 | Model Evaluation | Evaluation report | Adriana | 24/10 | 26/10 | 300
3.2 | Dashboard Development | Dashboard prototype | Team | 27/10 | 30/10 | 900
4.1 | Testing & Validation | Validated dashboard and model | Liyana | 31/10 | 2/11 | 750
4.2 | Report & Presentation | Final report and slides | Team | 3/11 | 8/11 | 1440
*Integration Notes:Model design because it is the most important part in a project since it determines the accuracy of the whole project