## Sheet1
TASK | WEEK
| OCTOBER | [6 empty] | NOVEMBER
Requirement Gathering | 6/10 - 8/10
Data Collection |  | 9/10 - 13/10
Model Design |  |  | 14/10 - 17/10
Model Training |  |  |  | 18/10 - 23/10
Model Evaluation |  |  |  |  | 24/10 - 26/10
Dashboard Development | [5 empty] | 27/10 - 30/10
Testing & Validation | [6 empty] | 31/10 - 2/11
Report & Presentation | [8 empty] | 3/11 - 8/11